## Master Sheet
Background ID | Map ID | Overworld Area | Needs a Background? | Background Status | Hardware Status | Background Author(s) | Notes on Peaches
22 |  | Route 19 Generic | TRUE | In Progress | Has Issues | Peaches | Back of route has strange green wall. Grass needs updated. Tree shadows clip floor. Texture season mismatch between path and regular grass. Fusion Flare etc extends over skybox.
23 |  | Route 20 Upper Generic | TRUE | In Progress | Has Issues | Peaches | Heavy overdraw in multibattles, minor in singles. Leaves float over the ground slightly. Grass needs updated. Tree shadows clip floor. Path clips between polys. Fusion Flare etc extends over skybox.
24 |  | Route 20 Lower Generic | TRUE | In Progress | Has Issues | Peaches | Grass needs updated to new style. Fences missing shadows. Distant trees need updating. Heavy overdraw in multibattles, minor in singles. The side walls should probably be broken up somewhat. Fusion Flare makes the screen grey.
25 |  | Flocessy Ranch Front | TRUE | In Progress | Has Issues | Peaches | Major overdraw across screen midsection. Slight cracks in the ground path. Fusion Flare extends over the skybox.
26 |  | Flocessy Ranch Back | TRUE | In Progress | Has Issues | Peaches | Major overdraw across screen midsection. Grass needs updated to new style. Ground floors look a little flat. Fusion Flare extends over the skybox.
27 |  | Pokemon Center Generic | TRUE | In Progress | Has Issues | Peaches | Missing vertex lighting. Nurse Joy looks a little funny, plant looks very 2D due to angle to camera.
28 |  | Alder's House | TRUE | In Progress | Has Issues | Peaches | Missing vertex lightning. Floating cushions + cushons. Floor is lowered.
29 |  | Pledge Grove | TRUE | In Progress | Has Issues | Peaches | Major overdraw in midsection. Ground flowers floating slighty, no pattern animations. Big tree when using Fusion Flare.
30 |  | Aspertia Gym Minor 1 | TRUE | In Progress | Has Issues | Peaches | Major overdraw in midsection. Playground items floating slightly.
31 |  | Aspertia Gym Minor 2 | TRUE | In Progress | Has Issues | Peaches | Major overdraw at the top of the screen. Floating gym items and leader platform. Overlook is in the wrong geograhical position. City background seems out of place.
32 |  | Aspertia Gym Major | TRUE | In Progress | Has Issues | Peaches | Catastrophic overdraw. Overlook platform looks out of place. Fusion Flare peeks over the skybox.
33 |  | Virbank Gate | TRUE | In Progress | Has Issues | Peaches | Gate floor clips the road. Gate attendant looks a bit out of place. House behind Pokemon Center window clips through the wall. Sea overlook is a bit bland. Trees inside the gate look a little strange.
34 |  | Virbank City Surf | TRUE | In Progress | Ignorable Issues | Peaches | Minor clipping on walls. Pipe shadow hovers over the water. Strong grey lines under the water. Strange grey view above the sidewalk.
35 |  | Virbank Pier (Day) | TRUE | In Progress | Ignorable Issues | Peaches | Fencing floating above the ground. Gap in water on the far right when camera pans. City light at night a little too bright.
36 |  | Virbank Pier (Evening) | TRUE | In Progress | Ignorable Issues | Peaches | Fencing floating above the ground. Gap in water on the far right when camera pans.
37 |  | Virbank Pier (Night) | TRUE | In Progress | Ignorable Issues | Peaches | Fencing floating above the ground. Gap in water on the far right when camera pans.
38 |  | Aspertia Outlook | TRUE | In Progress | Has Issues | Peaches | Entire scene shifted to the left. Major overdraw issues in the lower part. Fencing is floating and is not present at all on the left. Fusion Flare exposes the skybox edge.
39 |  | Virbank Complex (LOS) | TRUE | In Progress | Has Issues | Peaches | Grass needs updated to new style. Line of sight doesn't terminate nicely. Buildings have shadows clip into the floor. Minor overdraw in midsection of map. Overhead pipes look kinda bad. Fusion Flare exposes skybox edge.
40 |  | Virbank Complex (End) | TRUE | In Progress | Has Issues | Peaches | Grass needs updating to new style. Sea/skybox look very empty. Minor overdraw against move backgrounds.
41 |  | Virbank Gym (Floor) | TRUE | In Progress | Ignorable Issues | Peaches | Stage gear and stools are all floating slightly. Front speaks don't have a full shadow beneath them.
42 |  | Virbank Gym (Roxie) | TRUE | In Progress | Ignorable Issues | Peaches | Speakers have a purple line down the middle.
43 |  | Battle Company (1st floor) | TRUE | In Progress | Ignorable Issues | Peaches | Elevator door is floating slightly. Servers in top left and desk are also floating. Plant and pot have incorrect vertex colours.
44 |  | Battle Company (2nd floor) | TRUE | In Progress | Ignorable Issues | Peaches | Many floating furnatures and shadows. Elevator door floating again. Vertex colour issues on plant pot.
45 |  | Castelia Sewers (Generic) | TRUE | In Progress | Ignorable Issues | Peaches | Minor overdraw when sending mon out.
46 |  | Relic Passage (Castelia Side) | TRUE | In Progress | Ignorable Issues | Peaches | Back wall has slight gaps. No vertex colours. Could do with some details when the camera pulls back.
47 |  | Castelia Gardens | TRUE | In Progress | Ignorable Issues | Peaches | Grass needs to be updated to new style.
48 |  | Route 4 (W2, Entrance) | TRUE | In Progress | Ignorable Issues | Peaches | Fusion Flare exposes skybox edge. Slight clipping on Fusion Flare impact.
49 |  | Join Avenue (Entrance) | TRUE | In Progress | Ignorable Issues | Peaches | City background's monolithic grey appears as block colour, inappropriate for Nimbasa too.
50 |  | Route 4 (W2, Ruins) | TRUE | In Progress | Ignorable Issues | Peaches | Shadows clip into the floor. Fusion Flare exposes the skybox edge.
51 |  | Liberty Island (Day) | TRUE | In Progress | Ignorable Issues | Peaches | Tree shadows clip into the ground.
52 |  | Liberty Island (Evening) | TRUE | In Progress | Ignorable Issues | Peaches | Tree shadows clip into the ground.
53 |  | Liberty Island (Night) | TRUE | In Progress | Ignorable Issues | Peaches | Tree shadows clip into the ground.
54 |  | Castelia Fountain | TRUE | In Progress | Has Issues | Peaches | Tree textures do not have any transparency in the leaves.
55 |  | Castelia Gym (Generic) | TRUE | In Progress | Ignorable Issues | Peaches | Pod faces the camera instead of side on. When sending out mon, looks a little strange with the strings nearest the camera. Fusion Flare shows the ceiling to be a little weird.
56 |  | Castelia Gym (Burgh) | TRUE | In Progress | Has Issues | Peaches | Camera pulls through the wall to start battle, then pulls back through the paint/hole when sending out mon. Paint brushes and cans appear to be floating. Holes are seen through the floor. Fusion Flare causes palette issues on the users mon.
57 |  | Desert Resort (Route 4 Entrance) | TRUE | In Progress | Ignorable Issues | Peaches | Route gate clips harshly into the side wall. Skybox is very bland and contrasts quite harshly.
58 |  | Desert Resort (Relic Castle Entrance) | TRUE | In Progress | Ignorable Issues | Peaches | City background looks quite harsh. Very empty.
59 |  | Relic Castle (Downstairs) | TRUE | In Progress | Ignorable Issues | Peaches | Camera pulls back into the void when sending mon out. Fusion Flare shows skybox limit very clearly.
60 |  | Join Avenue (Interior) | TRUE | In Progress | Has Issues | Peaches | Fusion Flare causes a palette issue. Also populated when the entrance wasn't, but that's probably minor.
61 |  | Nimbasa City | TRUE | In Progress | Is Perfect | Peaches
62 |  | Route 5 (Bridge) | TRUE | In Progress | Has Issues | Peaches | Minor overdraw when sending out mons on either side, or when landing Fusion Flare.
63 |  | Route 5 (Forest) | TRUE | In Progress | Has Issues | Peaches | Major overdraw across the screen. Custom mountain asset. Fusion Flare shows skybox boarder.
64 |  | Route 16 (Road) | TRUE | In Progress | Ignorable Issues | Peaches | Needs new grass.
65 |  | Route 16 (Forest) | TRUE | In Progress | Has Issues | Peaches | Major overdraw across most the screen.
66 |  | Lostlorn Forest (Entrance) | TRUE | In Progress | Has Issues | Peaches | Major overdraw across the upper portion of the screen. Needs new grass.
67 |  | Lostlorn Forest (Back Area) | TRUE | In Progress | Has Issues | Peaches | Minor overdraw along back treeline. Fusion Flare exposes skybox edges.
68 |  | Nimbasa Gym (BW1) | TRUE | In Progress | Is Perfect | Peaches
69 |  | Nimbasa Gym (Catwalk) | TRUE | In Progress | Is Perfect | Peaches
70 |  | Nimbasa Gym (Elesa) | TRUE | In Progress | Ignorable Issues | Peaches | Slight clipping on stage floor. Clipping on screen shadows. Camera pans back into the crowd.
71 |  | Anville Town | TRUE | In Progress | Has Issues | Peaches | Light overdraw as battle begins. Stairs have incorrect texture mirroring.
72 |  | Driftveil Drawbridge | TRUE | In Progress | Has Issues | Peaches | Overdraw across middle screen when using Fusion Flare - otherwise looks good!
73 |  | Driftveil Island | TRUE | In Progress | Ignorable Issues | Peaches | Driftveil Gym and especially the Plasma House is floating. Island very rectangular cutoff. Bridge shadows overlap and cut into stairs, bridge markings and pillar tops are floating. Grey fence is floating too.
74 |  | Driftveil Plasma House (Exterior) | TRUE | In Progress | Has Issues | Peaches | Significant overdraw across middle of screen.
75 |  | ??? | FALSE | N/A | Untested | Peaches | Purple vanilla background?
76 |  | Driftveil Building | TRUE | In Progress | Ignorable Issues | Peaches | Plant pot doesn't seem to have vertex lighting? Trainer sprite drawn over the building pillar in awkward way.
77 |  | Driftveil Plasma House (Interior) | TRUE | In Progress | Ignorable Issues | Peaches | Plant pot doesn't seem to have vertex lighting?
78 |  | Route 6 | TRUE | In Progress | Has Issues | Peaches | Massive overdraw across screen. Wild grass needs updating to new style. River rock doesn't seem to be correctly animated.
79 |  | Route 6 (2?) | TRUE | In Progress | Has Issues | Peaches | Not sure what the difference between these two is. Massive overdraw across screen. Wild grass needs updating to new style. River rock doesn't seem to be correctly animated.
80 |  | Clay Tunnel | TRUE | In Progress | Ignorable Issues | Peaches | Fusion Flare creates a grey rectangle over the top half of the screen at the apex of the attack. Very ignorable though!
81 |  | Driftveil Gym (Generic) | TRUE | In Progress | Ignorable Issues | Peaches | Back rock wall needs to be made higher. Could maybe do with a visible tunnel bore?
82 |  | Driftveil Gym (Clay) | TRUE | In Progress | Ignorable Issues | Peaches | Backmost golden platform cuts into the purple conveyer belt. Back rock wall needs to be raised. Once more, could maybe do with a tunnel bore?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## List of All Backgrounds
Backgrounds | [6 empty] | Platforms
ID | Background Location | Author | Status | Seasonal | Versions | Needed For | ID | Platform Description | Used in? | Author | Status
0 | Aspertia Overlook | Both | Complete | Yes |  |  | 0 | Blank Platform | Most backgrounds | Peaches | Completed
1 | Aspertia City Fishing | Peaches | Needs Work | Yes |  |  | 1 | Water Platform 1 | Water Backgrounds | Peaches | Completed
2 | Generic Pokemon Center | Peaches | Needs Work | No |  |  | 2 | Water Platform 2 | Water Backgrounds | Peaches | Completed
3 | Route 19 | Peaches | Needs Work | Yes |  |  | 3 | Speakers 1 | Virbank Gym | Peaches | Completed
4 | Generic Pond Surf/Fishing | Peaches | Needs Work | Yes |  |  | 4 | Speakers 2 | Virbank Gym | Peaches | Completed
5 | Route 20 (West) | Both | Complete | Yes | Season |  | 5 | Bobbing Ship | Virbank Docks | Peaches | Completed
6 | Generic River Surf/Fishing | Peaches | Needs Work | Yes |  |  | 6 | Rollercoaster Car 1 | Old Nimbasa Gym | Peaches | Completed
7 | Flocessy Ranch South | Aphex | Complete | Yes |  |  | 7 | Rollercoaster Car 2 | Old Nimbasa Gym | Peaches | Completed
8 | Flocessy Ranch North | Peaches | Needs Work | Yes |  |  | 8 | Mining Platform 1 | Driftveil Gym Trainers | Peaches | Completed
9 | Alder's House | Both | Complete | No |  |  | 9 | Mining Platform 2 | Driftveil Gym Trainers | Peaches | Completed
10 | Pledge Grove | Peaches | Needs Work | Yes | Season |  | 10 | Yellow Mining Platform 1 | Driftveil Gym Leader | Peaches | Completed
11 | Aspertia Classroom | Aphex | Complete | No |  |  | 11 | Yellow Mining Platform 2 | Driftveil Gym Leader | Peaches | Completed
12 | Aspertia Gym Trainer A | Peaches | Needs Work | Yes |  | Cascade | 12 | Wailord | Marine Tube | Peaches | Completed
13 | Aspertia Gym Trainer B | Peaches | Needs Work | Yes |  | Cascade | 13 | Alomomola | Marine Tube | Peaches | Completed
14 | Aspertia Gym Leader | Both | Complete | Yes |  |  | 14 | Wind Turbines | Skyla Gym | Aphex | Completed
15 | Route 20 (East) | Peaches | Needs Work | Yes |  |  | 15 | Shauntel Books | Shauntel's Room | Aphex | Completed
16 | Virbank Gate | Both | Complete | Yes |  |  | 16 | Shauntel Wisps | Shauntel's Room | Aphex | Completed
17 | Virbank City (Streets) | Peaches | Needs Work | Yes |  |  | 17 | Giant Clock Relic | Iris Champion Room | Aphex | Completed
18 | Virbank Canals | Peaches | Complete | No |  |  | 18 | Janine 1 | Janine Battle | Peaches | Completed
19 | Virbank Docks (Day) | Both | Complete | No |  |  | 19 | Janine 2 | Janine Battle | Peaches | Completed
20 | Virbank Docks (Sunset) | Peaches | Complete | No
21 | Virbank Docks (Night) | Peaches | Complete | No
22 | Virbank Complex (Exterior) | Peaches | Needs Work | Yes
23 | Virbank Complex (Interior) | Peaches | Needs Work | Yes
24 | Virbank Preschool | - | Not Started | No |  | Cascade
25 | Virbank Gym (Trainers) | Both | Complete | No |  | Cascade
26 | Virbank Gym Leader | Peaches | Complete | No
27 | Pokestar Studios (Exterior) | - | Not Started | Yes |  | Cascade
28 | Pokestar Studios (Interior) | Aphex | Complete | No |  | Redux
29 | Virbank City (by Pokestar Gate) | Aphex | Complete | Yes |  | Redux
30 | Castelia City Streets | - | Not Started | No |  | Redux
31 | Castelia Cafe | Aphex | Complete | No
32 | Castelia Plaza | Both | Complete | Yes |  | Redux
33 | Castelia Building (Red Tile) | Both | Complete | No
34 | Castelia Building (Purple Tile) | Both | Complete | No
35 | Route 4 (South Streets) | Both | Needs Work | No | BW2
36 | Route 4 (Water) | Peaches | Complete | No
37 | Castelia Sewers | Peaches | Complete | No
38 | Castelia Sewer (Dried Out) | - | Not Started | No |  | Redux
39 | Castelia Sewer (Water) | Peaches | Complete | No
40 | Castelia Sewer (Chambers) | - | Not Started | No |  | Redux
41 | Castelia Back Alley | Aphex | Complete | No
42 | Castelia Gardens | Both | Complete | Yes
43 | Generic Cave Interior | Peaches | Complete | No
44 | Liberty Garden (Day) | Both | Complete | Yes
45 | Liberty Garden (Sunset) | Both | Complete | Yes
46 | Liberty Garden (Night) | Both | Complete | Yes
47 | Liberty Lighthouse Interior | Aphex | Complete | No |  | Redux
48 | Castelia Gym Trainers | Peaches | Complete | No
49 | Castelia Gym Leader | Both | Complete | No
50 | Route 4 (Middle) | Peaches | Complete | No | BW2
51 | Route 4 (Pre Pokestar) | Peaches | Needs Work | No
52 | Desert Resort (Exterior) | Peaches | Needs Work | No
53 | Desort Resort (Interior) | Peaches | Needs Work | No
54 | Relic Castle (Interior) | Both | Complete | No
55 | Join Avenue | Peaches | Needs Work | No |  | Cascade
56 | Nimbasa City | Aphex | Complete | Yes
57 | Nimbasa Boardwalk | - | Not Started | No
58 | Nimbasa Stadium | Aphex | Complete | No |  | Redux
59 | Battle Subway | - | Not Started | No |  | Redux
60 | Anville Town | Peaches | Needs Work | Yes |  | Cascade
61 | Route 5 (Streets) | Both | Complete | Yes
62 | Route 5 (Forest) | Peaches | Needs Work | Yes
63 | Route 16 (Streets) | Peaches | Needs Work | Yes
64 | Route 16 (Forests) | Peaches | Needs Work | Yes
65 | Hidden Grotto | - | Not Started | No |  | Redux
66 | Lostlorn Forest (Bridge) | Peaches | Needs Work | Yes
67 | Generic Pine River Surf/Fishing | Peaches | Needs Work | Yes
68 | Lostlorn Forest (Flower Field) | Peaches | Needs Work | Yes
69 | Nimbasa Gym (Old Gym) | Peaches | Complete | No
70 | Nimbasa Gym (Trainers) | Both | Complete | No
71 | Nimbasa Gym Leader | Both | Complete | No
72 | Driftveil Drawbridge | Peaches | Needs Work | No |  | Cascade
73 | Driftveil City | Peaches | Needs Work | Yes
74 | Driftveil City (by Church) | Aphex | Complete | Yes
75 | Driftveil Interior Buildings | Peaches | Needs Work | No |  | Cascade
76 | Plasma Sanctuary | Peaches | Needs Work | No
77 | Driftveil Norman | Aphex | Complete | Yes |  | Redux
78 | Janine Battle | Peaches | Complete | No |  | Cascade
79 | Clay Tunnel | Peaches | Complete | No
80 | Route 6 (South) | Peaches | Needs Work | Yes
81 | Driftveil Gym Trainer | Both | Complete | No
82 | Driftveil Gym Leader | Both | Complete | No
83 | Generic Cave Fishing/Surfing | - | Not Started | No
84 | Relic Sanctum (the lower floors) | Both | Complete | No
85 | PWT Interior | - | Not Started | No |  | Cascade
86 | PWT Arena | - | Not Started | No
87 | Plasma Frigate Deck | Aphex | Complete | No
88 | Iron Chamber | Aphex | Complete | No
89 | Chargestone Cave Entrance | Aphex | Complete | No
90 | Chargestone Cave (1F) | - | Not Started | No
91 | Chargestone Cave (B1F) | Aphex | Needs Work | No
92 | Route 7 | - | Not Started | Yes
93 | Celestial Tower (Base) | - | Not Started | No |  | Cascade
94 | Celestial Tower (Middle) | - | Not Started | No
95 | Celestial Rooftop | Aphex | Complete | No
96 | Twist Mountain (entrance) | Aphex | Complete | Yes |  | Redux
97 | Mistralton Gym Trainers | - | Not Started | No
98 | Mistralton Gym Leader | Aphex | Complete | No
99 | Reversal Mountain Outskirts | - | Not Started | No
100 | Strange House | - | Not Started | No
101 | Reversal Mountain | Aphex | Complete | No | BW2
102 | Reversal Heart | - | Not Started | No | BW2
103 | Route 14 | - | Not Started | Yes
104 | Undella Town (Alder) | - | Not Started | Yes |  | Cascade
105 | Undella Interior | - | Not Started | No |  | Cascade
106 | Generic Ocean Surfing/Fishing | - | Not Started | No
107 | Abundant Shrine | Aphex | Complete | Yes
108 | Generic Pine Pond Fishing/Surf | - | Not Started | Yes
109 | Marine Tube | Peaches | Needs Work | No
110 | Humilau City (Streets) | Aphex | Complete | No
111 | Humilau City (Surfing/Water) | - | Not Started | No
112 | Route 22 | - | Not Started | Yes
113 | Pinwheel Forest (Forest) | - | Not Started | Yes
114 | Rumination Field | - | Not Started | Yes
115 | Humilau Gym Trainers | - | Not Started | No
116 | Humilau Gym Leader | Aphex | Complete | No
117 | Abyssal Ruins | - | Not Started | No
118 | Abyssal Sanctum | - | Not Started | No
119 | Plasma Frigate Interiors | - | Not Started | No
120 | Frigate Kyurem Room (South) | - | Not Started | No
121 | Frigate Kyurem Room (North) | Aphex | Complete | No
122 | Route 13 (Beachs) | - | Not Started | Yes
123 | Lacunosa Town | Aphex | Complete | Yes
124 | Route 12 | Aphex | Needs Work | Yes
125 | Village Bridge (Bridge) | Aphex | Complete | Yes
126 | Village Bridge (Courts & Forests) | - | Not Started | Yes
127 | Striaton Restaurant | - | Not Started | No
128 | Route 11 | - | Not Started | Yes
129 | Opelucid City Streets | - | Not Started | Yes | BW2
130 | Route 9 | - | Not Started | Yes
131 | SM9 | - | Not Started | No |  | Cascade
132 | SM9 (Rotom) | Aphex | Complete | No |  | Yes
133 | Twist Mountain (Ice Chamber) | - | Not Started | No
134 | Twist Mountain (Basin) | - | Not Started | No
135 | Nature Preserve | - | Not Started | Yes
136 | Opelucid Gym Trainers | - | Not Started | No |  | Cascade
137 | Opelucid Gym Leader | Peaches | Complete | No | BW2
138 | Opelucid Frozen | - | Not Started | Yes | BW2
139 | Opelucid Zinzolin | - | Not Started | Yes
140 | Route 9 Frozen | - | Not Started | Yes
141 | Route 11 Frozen | - | Not Started | Yes
142 | Moors of Iccirrus | - | Not Started | Yes | Season
143 | Route 10 | - | Not Started | Yes
144 | Route 23 (Strength Rocks Area) | - | Not Started | Yes
145 | Route 23 (Valleys) | - | Not Started | Yes
146 | Giant Chasm (Basin) | - | Not Started | Yes
147 | Plasma Frigate (Hallway) | - | Not Started | No
148 | Plasma Frigate (Barracks) | - | Not Started | No
149 | Plasma Frigate (Kyurem's Room) | Aphex | Complete | No
150 | Plasma Frigate (Colress's Room) | Aphex | Complete | Yes
151 | Plasma Frigate (Ghetsis's Room) | Aphex | Complete | No
152 | Giant Chasm (Frozen Basin) | Aphex | Complete | Yes
153 | Deep Giant Chasm | Aphex | Complete | No
154 | Victory Road (Entrance) | Aphex | Complete | Yes
155 | Victory Road (Ruins) | - | Not Started | No
156 | Victory Road (Cliffs) | - | Not Started | Yes
157 | Victory Road (Hugh) | Aphex | Complete | No |  | Redux
158 | Pokemon League Entrance | - | Not Started | No |  | Cascade
159 | Old Victory Road | - | Not Started | No |  | Cascade
160 | N's Castle (N's Room) | - | Not Started | No |  | Cascade
161 | N's Castle (Throne Room) | - | Not Started | No |  | Cascade
162 | Shauntel's Room | Aphex | Complete | No
163 | Marshall's Room | Aphex | Complete | No
164 | Grimsley's Room | Aphex | Complete | No
165 | Caitlyn's Room | Aphex | Complete | No
166 | Iris's Room | Aphex | Complete | No
167 | Icirrus City | - | Not Started | Yes | Season
168 | Icirrus Gym | - | Not Started | No
169 | Dragonspiral Tower | - | Not Started | Yes | Season
170 | Dragonspiral Interior | - | Not Started | No
171 | Dragonspiral Peak | Aphex | Complete | No
172 | Underground Chamber | - | Not Started | No
173 | Ice Chamber | - | Not Started | No
174 | Stone Chamber | - | Not Started | No
175 | Pinwheel Forest (Exterior) | - | Not Started | Yes
176 | Route 3 | - | Not Started | Yes
177 | Striaton City | - | Not Started | Yes
178 | Dreamyard | - | Not Started | Yes
179 | Dreamyard (Lower Floors) | - | Not Started | No
180 | Route 2 | - | Not Started | Yes
181 | Route 1 (East) | - | Not Started | Yes
182 | Route 1 (West) | - | Not Started | Yes
183 | Route 17 (Shallows) | - | Not Started | No
184 | Route 18 (Beaches) | - | Not Started | No
185 | P2 Labaratory | - | Not Started | Yes
186 | Route 15 | - | Not Started | Yes
187 | Black City | - | Not Started | No |  | Redux
188 | Black Tower (Interior) | - | Not Started | No |  | Redux
189 | Black Sanctum | - | Not Started | No |  | Redux
190 | White Forest | - | Not Started | Yes
191 | White Treehollow | - | Not Started | No
192 | Treehollow Sanctum | - | Not Started | No
193 | Entralink | Aphex | Complete | No |  | Redux
194 | PWT (Battle Bros) | Aphex | Complete | No |  | Redux
195 | Unity Tower | Aphex | Complete | No |  | Redux
196 | Plasma Frigate Deck (Route 21) | Aphex | Complete | No
197 | Undella Town (Hugh) | Aphex | Complete | Yes |  | Redux
198 | Castelia Sewers (Grunt Battle) | Aphex | Complete | Yes
199 | Nimbasa Battle Facility | - | Not Started | No |  | Public Release
200 | Royal Unova | - | Not Started | No |  | Public Release
201 | Cave of Being | - | Not Started | No |  | Public Release
202 | Tubeline Bridge | - | Not Started | No |  | Public Release
203 | Marvelous Bridge | - | Not Started | No |  | Public Release
204 | Skyline Bridge | - | Not Started | No |  | Public Release